## Sheet1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - FULLY AUTOMATED FARMING SYSTEM
SB1/US1 | Web Application Access | SB1/D1/T1 | Creating web portal for system application | Dev & Ayush
|  | SB1/D1/T2 | Linking Database for the application | Dev & Ayush
|  | SB1/D1/T3 | Creating User accounts for Admins | Dev & Ayush
|  | SB1/D1/T4 | Creating User accounts for Farmers | Dev & Ayush
|  | SB1/D1/T5 | Testing the application | Dev & Ayush
|  | SB1/D1/T6 | Fixing Errors of the Same | Dev & Ayush
SB1/US2 | History of climate & Soil | SB1/D2/T1 | Getting climate condition from websites | Dev & Ayush
|  | SB1/D2/T2 | Fetching Data from Accuwhether to our portal | Dev & Ayush
|  | SB1/D2/T3 | getting history of soil condition of area from web portal | Dev & Ayush
|  | SB1/D2/T4 | Providing daily update for portal based on above data | Dev & Ayush
|  | SB1/D2/T5 | Testing the application | Dev & Ayush
SB1/US3 | Crops | SB1/D3/T1 | According to history and data find Suitable crops | Gaurav & Mahamid
|  | SB1/D3/T2 | Finding the appropriate crop from the selected crops | Gaurav & Mahamid
|  | SB1/D3/T3 | Getting Proper amount of crops to be planted | Gaurav & Mahamid
|  | SB1/D3/T4 | Testing the application | Gaurav & Mahamid
SB1/US6 | Pesticides | SB1/D4/T1 | Calculating the ammount of pesticides to be used | gaurav & Dev
|  | SB1/D4/T2 | Providing the amount of pesticides to be used to the farmer's application | gaurav & Dev
|  | SB1/D4/T3 | Providing time for pesticides to be spread | gaurav & Dev
|  | SB1/D4/T4 | Calculating the next time for providing pesticides | gaurav & Dev
|  | SB1/D4/T5 | Testing the application | gaurav & Dev
SB1/US7 | Soil Moisture | SB1/D5/T1 | Adding Soil sensor to the application | Ayush & mahamid
|  | SB1/D5/T2 | Connecting the sensor to the Arduino/pi | Ayush & mahamid
|  | SB1/D5/T3 | Fetching the data from sensor to the application via pi/arduino | Ayush & mahamid
|  | SB1/D5/T4 | Providing suggestion according to the data of soil. | Ayush & mahamid
SB1/US27 | Mobile Application | SB1/D6/T1 | Building mobile application for farmer | krishna
|  | SB1/D6/T2 | Connecting application to database | krishna
|  | SB1/D6/T3 | Providing all the info in the mobile application | krishna
|  | SB1/D6/T4 | Testing the application | krishna
|  | SB1/D6/T5 | Fixing Errors of the Same | krishna
SB1/US27 | Smoke Sensor | SB1/D7/T2 | Adding smoke sensor to the application | Krishna & kuldeep
|  | SB1/D7/T3 | Connecting the sensor to the Arduino/pi | Krishna & kuldeep
|  | SB1/D7/T4 | Fetching the data from sensor to the application via pi/arduino | Krishna & kuldeep
|  | SB1/D7/T5 | Providing suggestion according to the data of soil. | Krishna & kuldeep
SB1/US150 | Temperature sensor | SB1/D8/T1 | Adding Temperature sensor to the application | Krishna & kuldeep
|  | SB1/D8/T2 | Connecting the sensor to the Arduino/pi | Krishna & kuldeep
|  | SB1/D8/T3 | Fetching the data from sensor to the application via pi/arduino | Krishna & kuldeep
|  | SB1/D8/T4 | Providing suggestion according to the data of soil after calcualation | Krishna & kuldeep